# Honours Project Plan

|  |  |
| --- | --- |
| **Semester 1** | |
| 16th January 2019 | Began planning the project, created first iteration of this project plan document. |
| 21st January 2019 | Start weekly supervisor meetings |
| 16th January 2019 – 31st January 2019 | Fill in IPO form and submit |
| 17th January 2019 – 15th March 2019 | Literature Review |
| 1st March 2019 – 10th March 2019 | Prepare evidence of the work completed so far (with a draft of the chapters) and provide this to supervisor and the second marker. This is preparation for the interim meeting with the second marker. |
| 11th March 2019 – 29th March 2019 (Week 9-11) | Interim meeting |
| 15th March 2019 – 28th April 2019 | Implementation Phase 1 |
| 29th April 2019 – 11th May 2019 | Exams |
| **Summer ‘Holiday’** | |
| 11th May 2019 – 26th May 2019 | Break |
| 27th May 2019 – 9th September 2019 | Implementation Phase 2 |
| 15th July 2019 – 9th September 2019 | Start drafting & writing dissertation |
| **Semester 2** | |
| 10th September 2019 – 31st October 2019 | Implementation Phase 3 |
| 10th September 2019 – 12th November 2019 | Complete dissertation. Print & bind. |
| 12th November 2019 – 27th November 2019 | Create poster |
| ASAP, deadline: 27th November 2019 | Final submission |
| 27th November 2019 | Poster Session (13:00-17:00 JKCC) |
|  |  |